## Bug Report
Bug ID | Test Case ID | Description/Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority
Opencart_BUG_01 | TC_RF_08 | User is able to register an account by providing an invalid phone number | 1. Open the Application URL 2. Click on 'My Account' dropmenu 3. Select 'Register' option 4. Enter the new User valid details into the 'Register Account' page 5. Select the 'Privacy Policy' checkbox option 6. Click on 'Continue' button | Error message: invalid phone number | Warning message is not getting displayed, instead an Account is getting created with the given invalid phone number | Major | P0
Opencart_BUG_02 | TC_RF_09 | Red * sign for all the mendatory fields is not only visible for Privacy Policy Field | Go to Register > Check the Fields - First Name, Last Name, E-Mail, Telephone, Password, Password Confirm and Privacy Policy | All the specified Fields in the Test Steps should be marked with red color * symbol | Privacy Policy Field is not marked with red * Symbol. | Minor | P2
Opencart_BUG_03 | TC_LO_003 | Logout from one device does not log out the same account on another device | 1. Logout from Firefox. 2. Try accessing Account on Chrome. | User logged out on both devices. | User is not getting logged out on other device. | Medium | P1
Opencart_BUG_04 | TC_ATC_08 | Invalid quantity (-1) for Add to Cart shows success message instead of error | 1. Search for “iMac”. 2. Click product. 3. Enter quantity “-1”. 4. Click “Add to Cart”. | Error: “Invalid quantity.” | Error Message not shown instead Success Message: Product is added to cart shown | Critical | P0
Opencart_BUG_05 | TC_MA_005 | While Navigating to My Account from Site Map,Clicking My Account from Site Map logs out user with invalid token session warning | 1. Click “Site Map” in footer 2. Click “My Account” link | User lands on My Account page | User got logged out and Warning: Invalid token session. Please login again! Shown. | High | P2
Opencart_BUG_06 | TC_SC_007 | Updating Shopping Cart with invalid quantity (-1) shows success message instead of warning | 1. Enter product name in Search box 2. Click search icon 3. Click product 4. Click 'Add to Cart' 5. Click 'shopping cart!' 6. Enter negative/zero/non-numeric in Quantity 7. Click 'Update' | Proper warning message should be displayed informing the User to provide a postive numberical value | Wrong Messge like this Success: You have modified your shopping cart! Is shown | High | P2